## NEW Version
PROJECT FEASIBILITY SUMMARY
Local Highway Improvement (LHI) Initiative
Applicant | Over Parish Council |  |  | Status
Application Reference No | 73 |  |  | Version | 1
Assigned Highways Officer | Nicki Mason |  |  | Approved by: | LMA
Location of proposal | Long Furlong, Over
Streetview Link | Long Furlong
Application received | Original Application. **Needs clarity. - IF A CHANGE THROUGH FEASIBILITY THEN THIS NEEDS TO BE HERE AS A INTRODUCTION PARAGRAPH.
Feasibility Section
Officers Introduction / Overview | Over Parish Council is applying for the installation of a zebra crossing outside Over Primary School on Long Furlong. This location is a critical pedestrian route used daily by primary and secondary school children, parents, and residents accessing the nearby bus stop. The proposed crossing aims to address significant safety concerns and improve accessibility for vulnerable users, including elderly residents and those with mobility or sensory impairments. The scheme supports Cambridgeshire County Council’s objectives for safer routes to school, encouraging sustainable transport, and improving public health outcomes.
Highway Issue or Improvement - | There is currently no formal crossing point on this section of Long Furlong, despite high pedestrian demand, particularly during school peak times. Pedestrians are required to cross at informal locations, where visibility and driver compliance may be inconsistent. This results in: Increased risk of pedestrian/vehicle conflict Difficulty for children travelling independently to school Accessibility challenges for vulnerable users Safety concerns for bus users crossing the road
Key Considerations - | Proximity to Over Primary School and pupil movement patterns Traffic speed and volume on Long Furlong Visibility for both pedestrians and approaching vehicles Existing pedestrian desire lines and crossing behaviour Access to the nearby bus stop
Scheme concept proposed for LHI funding: | Installation of a zebra crossing on Long Furlong outside Over Primary School, including: Belisha beacons Road markings and high-friction surfacing Tactile paving for accessibility compliance Associated signage and illumination (if required)
Other options considered - | Informal crossing points – considered insufficient due to lack of priority for pedestrians Pedestrian refuge island – may not provide adequate safety given crossing demand and road width Traffic calming alone – would not provide a dedicated safe crossing facility
Key project risks - | Budget constraints or cost inflation affecting deliverability Construction timing constraints (e.g. school term impacts) Visibility or design limitations identified during detailed design phase Utility conflicts requiring adjustments
CCC Road Safety Team comments: (if required) | Current keep clear markings would need to be removed as they would conflict with Zebra markings. Could also look at some parking restrictions along during school drop off and pick up times to assist with visibility during peak times crossing in use.
TECHNICAL APPRAISAL OF PROPOSED SOLUTION
Does the application address a known problem, or safety issue? |  |  |  |  | RAG
The proposal addresses a clear and well-defined pedestrian safety issue at a location with high footfall, particularly during school peak periods. There is currently no formal crossing facility, despite regular use by children, families, and other vulnerable users. Informal crossing behaviour indicates an established desire line, confirming the presence of an existing safety concern. |  |  |  |  | g
Could the suggested scheme increase safety for highway users? |  |  |  |  | RAG
A zebra crossing would provide a designated, priority-controlled crossing point, improving driver awareness and compliance. This is expected to reduce pedestrian/vehicle conflict and enhance safety for all users, particularly schoolchildren and those crossing to access the nearby bus stop. |  |  |  |  | g
Could the scheme contribute positively to public health? |  |  |  |  | RAG
The scheme encourages active travel by making walking routes safer and more attractive, particularly for school journeys. Improved accessibility also benefits older residents and those with mobility or sensory impairments, supporting wider public health and wellbeing objectives. |  |  |  |  | g
Does the application have demonstrable local support?
The application is submitted by Over Parish Council, indicating local governance support. However, further evidence such as consultation feedback, petitions, or school endorsement would strengthen the case and provide clearer demonstration of broader community backing. |  |  |  |  | a
Could the scheme potentially lead to any localised environmental improvements? |  |  |  |  | RAG
By supporting walking and reducing reliance on short car trips for school access, the scheme has the potential to contribute to reduced local congestion and emissions during peak times, resulting in minor but positive environmental benefits. |  |  |  |  | g
Value for Money - (Effectiveness) |  |  |  |  | RAG
The cost of a zebra crossing is significantly more than the contribution from the parish and the maximum contribution from the LHI fund. Additional funding would be required to enable delivery of this scheme. It could be justified due to the high level of daily pedestrian use and its direct safety benefits. The scheme provides a targeted intervention at a known desire line, maximising impact for the investment. Also the footway on the oposite side from the school should be extended depending on the exact location of the zebra crossing. This has not been factored into pricing as unsure of the length required and already over budget for funding currently available.
Deliverability (Risks to Delivery, see 'Key project risks' section above for further information) |  |  |  |  | RAG
While the scheme is relatively straightforward, there are potential risks relating to detailed design requirements, visibility constraints, and statutory processes such as Traffic Regulation Orders. These risks are considered manageable but may impact programme timelines. The funding is also a risk for delivery especially as it is significantly over budget.
ESTIMATED CONSTRUCTION & OTHER COSTS
Item |  |  |  | Estimated Cost
CCC Officer and Staff cost |  |  |  | 7903.06
Construction cost (Inc. Traffic Management) |  |  |  | 48000
TTRO if required |  |  |  | 1579
Safety Audit (Stages 1-3)if required |  |  |  | 1768
Legal Traffic Regulation Order (includes 2no. newspaper adverts) |  |  |  | 1000
Sub-Total |  |  |  | 60250.06
23% Risk Contingency |  |  |  | 13857.5138
|  |  | GRAND TOTAL | 74107.5738
Project Budget Required | 74107.5738
Applicant contribution: | 20000 | £ | 26.99% |  | % | The applicant will need to increase contribution where possible, or other funding sources sought
CCC contribution: | 54107.5738
Project duration: | 18 months (commencing 2nd November 2026)